ADDENDUM 5

Plans, Education, Equipment, Other

Please complete all paperwork for your _________project.

Any missing information and the entire application may be returned and it may become ineligible.

Project Work Schedule  Application IX. Page 7

Please adjust  these examples to your individual project, not all steps may be used or you may have different ones. It also depends how large your project is, for the length of time each step will take.

Please refer to these steps on your Quarterly Reports and this will help you determine what percentage of your project is finished.

Work needs to commence within 90 days after approval and finish the project 18 months after approval date. (See original approval letter from FEMA for this date).

Based on an average project- some steps may occur simultaneous.  Try to include steps for which there is a cost (ie.  materials, etc)

PLEASE USE THIS AS ONLY A GUIDE FOR EACH  PROJECT TYPE.

Activity                                                                                 Timeframe

Project is Approved

“PLANS”

Plan Services, Create Working committee                                                         1 Month

Receive & Distribute to Group a Sample Plan/SOG                                         1 Month

Group Meetings assign work                                                                               1 Months

Collect Data, Get maps, GIS Information                                                          1 Month

Send out Draft Plan for Comments                                                                     1 Month

Changes to draft, Review Changes                                                                      1 Month

Draft to a final Plan/comments                                                                            2 Month

Hard Copy & Digital Copies of Final  Plan                                                        1 month

Final Draft Plan to Public Meetings                                                                    2 months

Communities adopts plan/Resolution of Plan                                                     2 months

Send Final Plan to PEMA & FEMA For approval                                            2 Months

Final Changes If necessary  Publication                                                              1 Month

“EQUIPMENT “(Emergency/Other)

Order Equipment  (Radios) ,   Publish Training materials                                2 Months

Receive Equipment,   Train Facilities                                                                  4 months

Provide ongoing Public Education /training                                                     12 months

“EDUCATION”

Order Educational Materials                                                                                1 Month

Receive Materials, Plan training                                                                          3 months

Disseminate Materials & Training                                                                       4 Months

Follow-up of Training                                                                                       3- 9 Months

Project Completed