ADDENDUM 4

STRUCTURAL

Please complete all paperwork for your Structural project.

Any missing information and the entire application may be returned and it may become ineligible.

Project Work Schedule  Application IX. Page 7

Please adjust these examples to your individual project, not all steps may be used or you may have different ones. It also depends how large your project is, for the length of time each step will take.

Please refer to these steps on your Quarterly Reports and this will help you determine what percentage of your project is finished.

Work needs to commence within 90 days after approval and finish the project 18 months after approval date. (See original approval letter from FEMA for this date).

Based on an average project- some steps may occur simultaneously.  Try to include steps for which there is a cost (ie. engineering , design, materials, etc)

PLEASE USE THIS ONLY AS A GUIDE.

Activity                                                                                          Timeframe

Project is Approved

Public Meetings, Engineering, design                                                                      4 Months

Permit Applications, Bid specifications                                                                   2 months

Permits received, permits reviewed, Bid process                                                    3 Months

Redesign work                                                                                                            2 Month

Upgrades, installation and Construction completed                                               4 Months

Testing of upgrades                                                                                                    2 months

Closeout

Project Completed                                                                                       18 months